## Crew Details
SL.No | Department | Sub-Department | Supervisor | Crew Name | Project Description | Activity | Location
1 | Civil | Site | Ashish | Thabasmani | MPP Reliability improvement Project | VFD Building-fdn deShuttering, Curing and Coating Preparation Works | G-Stn
2 | Civil | Site | Ashish | Easwaran | AEP Project | Heater area- Grade slab loose soil removal & PCC Preparation | MMPS
3 | Civil | Site | Ashish | John | AEP Project | Tank area-Drain Pit rebar and Shuttering Works | MMPS
4 | Civil | Site | Ashish | Chandra (Al-Mahri) | AEP Project | Tank area-PS fdn Excavation & GRE trench Excavation | MMPS
5 | Civil | Site | Ashish | Rana Qasim (Al-Mahri) | AEP Project | Electrical Cable trench Excavation | MMPS
6 | Civil | Site | Ashish | Shoeb | MGCP Project | Area backfilling, levelling and compaction works | MMPS
7 | Civil | Site | Ashish | Basudev | HPWI Pump Project | Fence Relocation Works, Pump fdn PCC Curing Works | DWD
8 | Civil | Site | Ashish | Ravindra | HPWI Pump Project | VFD Building - Plastering & Coating Preparation, Scaffolding Erection | DWD
9 | Civil | Site | Ashish | Jerod | SS-06 Replacement Project | Fence Demolition Works | MMPS
10 | Civil | Site | Ashish | Asif | Qata Scale Inhibitor Project | A-451004 Slope protection Works | Qata
11 | Civil | Site | Ashish | Gouse Pasha | AEP/MGCP Project | BorrowPit Works | Borrow pit-7
12 | Civil | Precast Yards | Ashish | Jitendra | Rahab Polymer/AEP/HP Pump | Pipe support/access barrier foundation protective coating /rebar works | Precast yard
13 | Mechanical | Site | Khalid | Rafi | AEP Project | A-24209-Pipe support installation, valve and grating installation, etc. | MMPS
14 | Mechanical | Site | Shiva | Sanjay | AEP project | Pipe rack spool installation and welding | MMPS
15 | Mechanical | Site | Shiva | Nagaraj | AEP Project | Scaffolding Erection for Piping Works | MMPS
16 | Mechanical | Site | Shiva | K.P Anil | AEP Project | Tank form area-Pipe support Structure installation works Piping spool installation and welding | MMPS
17 | Mechanical | Site | Shiva | Jaffer | AEP Project | Heater area- Drain line support installation | MMPS
18 | Mechanical | Site | Shiva | Nasser | GFT Project | Scaffolding Erection & Tie-in Preperatory Works | QHR
19 | Mechanical | Fabshop / Yard - NIMR/ Marmul | Urithevan | Anil J Nair | AEP Project | Pipe support structure modification Works, Shoe Support Fabrication, Pipe spool loading/Unloading Works,Scaffolding material seggregation Works,HW Polymer Flood Project | BEC Yard
20 | E&I | Site | Godwin | Arun | AEP Project | A-24209/A-24210 RCU Support modification,fabrication,installation and Earthing | MMPS
21 | E&I | Site | Godwin | Saquib Ali | AEP Project | Support Welding | MMPS
22 | E&I | Site | Godwin | Venkat | AEP Project | Support Welding | MMPS
23 | E&I | Site | Prasanna | Shinu | SS-06 Replacement Project | SS-02 Load Change Over activities | MMPS
24 | E&I | Site | Prasanna | Jadhav | SS-06 Replacement Project | SS-02 Load Change Over activities | MMPS
25 | E&I | Site | Prasanna | Aneeth | STS Office Facility | STS office facility Permanent Pwoerup & OHL Works | Near STS office
26 | E&I | Site | Ajay | Ravinder Singh | AEP Project | Instrument Cable laying | MMPS
27 | E&I | Site | Ajay | Shiva | AEP Project | A-24209 Instrument cable laying,Cable Glanding,dressing & Instrument tubing , Instrument installation Works | MMPS
28 | E&I | Site | Ajay | Dominic | AEP Project | A-24210 Instrument cable laying,Cable Glanding,dressing & Instrument tubing , Instrument installation Works | MMPS